## Launch Overview
Field | Value
Product Name | Aurora AI Analytics Platform
Launch Date | September 15, 2026
Target Markets | AMER, EMEA, APAC
Revenue Target Year 1 | $4.2M ARR
Overall Status | Amber — On Track with 3 Blockers
Launch Owner | Priya Nair (VP Product)
Program Manager | James Okonkwo
Executive Sponsor | CEO — Rachel Voss
Last Updated | August 11, 2026
Days to Launch | 35

## GTM Checklist
# | Task | Owner | Department | Deadline | Status | Blocker
1 | Finalize product positioning and messaging | Priya Nair | Product | Aug 15 | Complete
2 | Create launch press release | Sofia Reyes | Marketing | Aug 18 | On Track
3 | Record product demo video (3 min) | Tom Bradley | Marketing | Aug 20 | In Progress
4 | Sales enablement training deck | Ken Watanabe | Sales | Aug 22 | On Track
5 | Pricing approval from Finance | James Okonkwo | Finance | Aug 14 | Blocked | CFO approval pending — waiting on Q3 reconciliation
6 | Legal review of EULA & ToS | Dana Hoffmann | Legal | Aug 16 | At Risk | Legal team bandwidth — 2 lawyers on leave
7 | Partner enablement kit distribution | Carlos Vega | Partnerships | Aug 25 | On Track
8 | Website landing page live (staging) | UI/UX Team | Engineering | Aug 28 | Complete
9 | Beta customer feedback synthesis | Anita Desai | Product | Aug 15 | Complete
10 | Analyst briefings (Gartner, Forrester, IDC) | Elena Kovacs | Marketing | Aug 20 | On Track
11 | Customer reference program (3 quotes) | Maya Singh | CX | Aug 22 | At Risk | Apex escalation may affect reference willingness
12 | Social media campaign assets | Liam Chen | Marketing | Aug 25 | Complete
13 | Email nurture sequence (5 emails) | Sofia Reyes | Marketing | Aug 22 | On Track
14 | Paid media plan & budget sign-off | Liam Chen | Marketing | Aug 14 | Blocked | Budget approval pending Finance sign-off
15 | APAC localization (Japanese, Korean) | APAC Team | Marketing | Sep 1 | On Track
16 | EMEA GDPR compliance check | Dana Hoffmann | Legal | Aug 20 | At Risk | GDPR addendum review in progress
17 | CRM opportunity tagging for pipeline | Ken Watanabe | Sales | Aug 18 | Complete
18 | Support runbook & escalation playbook | Support Lead | CX | Aug 28 | In Progress
19 | API documentation published (dev portal) | Eng Docs Team | Engineering | Sep 1 | Complete
20 | Internal launch announcement (all-hands) | Comms Team | Comms | Sep 12 | On Track
21 | Executive talking points document | Rachel Voss | Executive | Sep 5 | Complete
22 | Launch webinar infrastructure & invites | Events Team | Marketing | Sep 8 | On Track
23 | Competitive battlecards update | Product Marketing | Marketing | Aug 20 | Complete
24 | Cloud marketplace listings (AWS, Azure, GCP) | James Okonkwo | Engineering | Sep 5 | Blocked | Azure Marketplace review SLA extended by 2 weeks
25 | Post-launch retrospective template | Priya Nair | Product | Sep 20 | On Track

## Stakeholder Map
Name | Role | Department | RACI | Email | Last Update | Action Needed
Rachel Voss | CEO / Executive Sponsor | Executive | A | r.voss@aurora.ai | Aug 11 | Approve final messaging by Aug 18
Priya Nair | VP Product / Launch Owner | Product | R | p.nair@aurora.ai | Aug 11 | Daily standup lead
Thomas Müller | CFO | Finance | A | t.mueller@aurora.ai | Aug 10 | Approve pricing & paid media budget
James Okonkwo | Program Manager | PMO | R | j.okonkwo@aurora.ai | Aug 11 | Track GTM checklist, escalate blockers
Sofia Reyes | Head of Marketing | Marketing | R | s.reyes@aurora.ai | Aug 9 | Finalize press release & email sequence
Ken Watanabe | VP Sales | Sales | C | k.watanabe@aurora.ai | Aug 8 | Confirm sales readiness by Aug 22
Dana Hoffmann | General Counsel | Legal | A | d.hoffmann@aurora.ai | Aug 7 | EULA & GDPR review — urgent
Elena Kovacs | Analyst Relations Lead | Marketing | R | e.kovacs@aurora.ai | Aug 10 | Schedule Gartner & Forrester briefings
Carlos Vega | Head of Partnerships | Partnerships | C | c.vega@aurora.ai | Aug 6 | Distribute partner kit by Aug 25
Anita Desai | Director, Product Mgmt | Product | R | a.desai@aurora.ai | Aug 11 | Beta synthesis complete — share with sales
Liam Chen | Performance Marketing Mgr | Marketing | R | l.chen@aurora.ai | Aug 9 | Pending budget approval for paid media
Maya Singh | Director, CX | CX | C | m.singh@aurora.ai | Aug 8 | Secure 3 customer references — at risk

## Launch Brief Data
Section | Content
Value Proposition | Aurora AI Analytics Platform empowers enterprises to transform raw data into real-time decisions with AI-native dashboards, predictive insights, and natural language querying — 10x faster than traditional BI tools.
Target Persona | Primary: Data-driven VP/C-level executives in mid-market & enterprise (500–10,000 employees) in Financial Services, Healthcare, and Tech verticals. Secondary: Analytics engineers and Data leads who champion tools.
Competitive Position | Positioned above Tableau and Power BI on AI capabilities; below Palantir on price. Unique differentiator: zero-code AI query builder and native M365/Salesforce/SAP connectors out of the box.
Pricing Strategy | SaaS subscription: Starter $2,500/mo (up to 10 users), Professional $7,500/mo (up to 50 users), Enterprise custom pricing. Annual discount 20%. Marketplace listings on AWS, Azure, GCP at GA.
Key Messages | 1) 'Insights in seconds, not days' — speed of AI vs legacy BI. 2) 'Your data speaks — Aurora listens' — NL query UX. 3) 'Launch in a week, not a quarter' — rapid deployment story. 4) Trusted by 3 Fortune 500 beta customers. 5) Built for compliance: SOC2 Type II, ISO 27001, GDPR-ready.